## Admin
Modules | Tasks | Tasks Weight (Story points) | Module weight (Story point) | Status | Module Completion (Story point) | Allocated Hrs | Utilized Hrs | Module completion (%)
Discovery | Product feature design and scoping | [5 empty] | 82.19
Platform setup | Initial platform setup | [5 empty] | 20
Project Managment | [6 empty] | 36.4
Syncup call/Demo/meetings | [6 empty] | 121.78
QA | [6 empty] | 243.25
Bug Fixing | [6 empty] | 7.96
Devops | [6 empty] | 4.35
Stock Transfer | Request list
Transfer history
| Create single SKU transfer | [5 empty] | 5
Bulk SKU transfer via CSV
Admin approve/reject
Background inventory update process
Transfer request details page
Authentication | Admin login | [5 empty] | 16.25
| Warehouse login | [5 empty] | 5
Forgot/Reset Password
Warehouse | Manage location (Enable/Disable & changes)
| Manage GST number | [5 empty] | 4.25
| Servicable pincodes for shipping Import & Export | [5 empty] | 11
| Driver assignment | [5 empty] | 5
| Vehicle assignment | [5 empty] | 5
Driver Management | Driver list | [5 empty] | 7.5
Create/Invite/Update/active/de-active/driver
Driver details
Vehicle Management | Vehicle list | [5 empty] | 6
Create/Update vehicle
Vehicle details
Platform Configurations | Brand | [5 empty] | 10
Category
Production/Catalogue setup (20-50 products)
Brand Management | List of brands | [5 empty] | 6.5
Create/Update/Delete/Active/De-active Brands
Product Management | Product -> Brand selection
| Product -> Custom Attributes changes (Remove sync) | [5 empty] | 5
| Import/Export changes | [5 empty] | 9
Map brand with product
RBAC | Plugin Integration with Role and Permissions | [5 empty] | 14
| Assign Warehouse Users to stock location | [5 empty] | 3.25
| Warehouse login | [5 empty] | 5
User Management | List of Users | [5 empty] | 8
User create/update/delete/active/de-active/
Loyalty Program (Reward Points) | Earn rule For Invite User | [5 empty] | 7.5
Earn rule Sign up user
| Earn rule for Purchase Order | [5 empty] | 9.46
Coneversion rate
Burn Rule
Fees Configuration | Shipping charge configuration | [5 empty] | 5
| Min order amount configuration | [5 empty] | 4
OMS | Order list with search, sort, filter and export
Order Details -> General informtion
Order confirmation & cancellation
Order assignment to warehouse
Order Detailes -> Order status tracking
Order Details -> Price Summary
Order Details -> Customer detail
Order Details -> Create and Download Invoice
Reporting/Analytics | Expense Report with date and warehouse filters
Sales report with date, Warehouse, Product, Category
Export reports
CMS | Policy Pages | [5 empty] | 1.5
| FAQs | [5 empty] | 6
| About Us | [5 empty] | 1.5
Banners
Multilanguage
Customer Support | List of raised query
Update status & Add note
Trip/Ride Management | List of all rides (Pending, Ongoing, Delivered)
Ride Detail
Audit Logs | System Logs
Transaction Management | List of transaction with status
Notifications | List of notification (enable/disable) with their triggers (Email, SMS, Push and In-APP Notifications)
Customer Management
Coupon & Promotion management
Mobile App API expose | Mobile App API expose | [5 empty] | 44
720.64

## Rider App
Modules | Tasks | Tasks Weight (Story points) | Module weight (Story point) | Status | Module Completion (Story point) | Allocated Hrs | Utilized Hrs | Module completion (%)
Authentication | Login
Logout
OTP verification
Resend OTP
Home | Order and Ride Counts
Active Ride with Order list
Create ride | Choose order
Choose vehicle
Rider list | List of complted & Upcoming Ride
Start Ride/Complete rider
Ride detail | Order list
Order detail | Order detail
Update Status
Collect payment Payment
Rider App API